## Sheet1
Daniel, Kim & Anatoly Log
Vecka | Datum | Aktivitet | Kommentarer | Tid (h)
v42 | 16-17/10-2013 | We discussed various topics and shared contact information. Created a dropbox profile. Wrote project proposal. | We got along well, and choosed to work with penetration tools of security. We gave each other our phone numer and Skype names. We also created a dropbox profile where we can store our files etc. We also sent in our project proposal. | 2 hour
v44 | 28/10-2013 | Feedback of our project proposal. Discussed some tools Anatoly will use for Wifi penetration. | We started of by discussing some of the feedback we got on our projekt proposal. We will til the next meeting fix what's missing. Anatoly has also choosed to work with Wifi Vulnerabilities and Attacks and will use BackTrack 5 R2 (Wifi wep cracking, wifi wpa/2 cracking, deauth users, packet sniffing, packet injections). | 20 min
v44 | 30/10-2013 | Research of some penetration tools. Timeplan and project plan | Kim and Daniel discussed and did some research about penetration tools. Should we do something together? Or work with tools by ourself as we are three in our project group? We also discussed a little bit about how our project plan and future work will look like. | 40 min
v44 | 1/11-2013 | Timeplan. Tools | Kim and Daniel started to work with the timeplan. Kim and Daniel also choosed respective topic to work with (Metasploit and Nmap). | 2 hours
v44 | 2/11-2013 | Timeplan. Preparation for the presentation. | By discussing thru Skype we finished our Timeplan and started to work on our powerpoint presentation. | 20 min
v44 | 3/11-2013 | Preparation for the presentation | We finished our powerpoint presentation and decided what time and place we would meet before the presentation starts (6 november). | 6 hours
v45 | 6/11-2013 | Main goal and main problem | After some feedback and afterthoughts from the presentation we decided to choose a main goal and main problem in common. Kim and Daniel started to discuss again what tools we can work with. | 5 hours
v45 | 8/11-2013 | Nmap, Wireshark and Metasploit | The tools Kim and Daniel has choosed to work with on the cabled network part is going to be Nmap and Wireshark, but also Metasploit as a bonus (for fun test). | 2 hours
v46 | 12/11-2013 | How to write a report | Kim and Daniel went to the short lecture on how to write a report. As Anatoly live in Norway and the lecture wasn't mandatory Kim and Daniel recorded the lecture and then sent it to Anatoly. | 1 hours
v46 | 14/11-2013 | Cracked WEP 64 and 128 bit | Anatoly has started to crack WEP 64 and 128 bit | 5 hours
v46 | 15/11-2013 | Hacked WPA and WPA2 | Anatoly has finnished to crack WEP 64 and 128 bit and also WPA and WPA2. | 7 hours
v47 | 18-20/11-2013 | Introduktion - background, goal, objective & methodology | We've started to work with our introduktion.
v47 | 20-26/11-2013 | Introduktion. Feedback. Method & Results | We sent in our introduktion for feedback and also got group 1 introduktion to give feedback to. Anatoly also started to work with method and results.
v48 | 27/11-2013 | Sniffing passwords. Prepere Switches and Routers. VLAN Abuse | Anatoly informs Kim and Daniel that he is done with the sniffing part where i has sniffed facebook passwords. Kim and Daniel have started to prepere the cisco equipment for there test with VLAN Abuse
v48 | 28/11-2013 | Method & results. VLAN Abuse | Anatoly continue to work with the Method and Results part. Kim and Daniel went to the university to continue the testing with BackTrack. | 4 hours
v48 | 29/11-2013 | Feedback | Today we all went to the group meeting for feedback. We got very good feedback, that we had to change some part in the introduction and also that we have to decide if we should split the projekt into two parts (as Anatoly can't write in swedish) or if we are going to write the whole project in english. We choosed to write the project in english. | 7 hours
v48 | 29-30/11-2013- | VLAN Abuse | Kim and Daniel continue to work with VLAN Abuse. Anatoly joined later on via Skype and Teamviewer to help. | 14 hours
v48 | 1/12-2013 | VLAN Abuse. Password sniffing. Metholodgy and Results | Anatoly and Daniel continues to work with the metholodgy and results in the background. Kim and Daniel (and Anatoly thru Skype and Teamviewer) coninue to test VLAN Abuse. But the test failed and we decided to start over with new topology and new configurations on the switches and routers. We also decided that we hade two computers with BackTrack. Kim mailed Olga and asked if he can borrow some computers. Kim and Daniel also start to work with password sniffing from the cisco devices | 10 hours
v50 | 2/12-2013 | VLAN Abuse. Password sniffing. Metholodgy and Results. Presentation | Kim got an answer from Olga that we could borrow some computers. Kim and Daniel continue to work with the test. Kim and Daniel also start to work with password sniffing (sniffing telnet-password and log login information from when a user login to the router via the webbrowser. Anatoly continue to work with Metholodhy and Results. Anatoly also finnsh the part in our powerpoint presentation that he will talk about in the presentation 4 december. | 10 hours
v50 | 3/12-2013 | Presentation. VLAN Abuse. Ebook | Kim and Daniel finnish the last part in the powerpoint presentation for tomorrow. They also got some time over to go to university for some more test on VLAN Abuse part. Olga also sent us an ebook of network cracking and hacking to read. | 10 hours
v50 | 4/12-2013 | Presentation. Feedback | Today we had the presentation where we present our metholodgy and results so far. It went all good, no critics. We also got some feedback of our new introduction we changed after the first feedback. | 3 hours
v50 | 5/12-2013 | Feedback. Method & Results | Daniel and Anatoly started to change what we had to change after the feedback we got on our updated introduction. Kim started to write the metholodgy and results for the cabled part. Kims computer also died later that night so a little bit of the text he wrote got erased. | 5 hours
v50 | 6/12-2013 | Method & results | Kim continue to write the method and results for the cabled part on his backup laptop. Daniel and Anatoly continued to change som part of the introduction and wifi method and results. | 5 hours
v50 | 7/12-2013 | Method & Resuts | Kim continue to write the method and results for the cabled part. Daniel and Anatoly continu to change some part at the wifi part. | 9 hours
v50 | 8/10-2013 | Method & Results | Kim finished the cabled part. Daniel created a todo-list what we have to do til 12th december. Anatoly tell us that he is ill, but will help as much he can. | 7 hours
-
Totalt: